## Sheet1
| One year | 9 months | 6 months | 4 months | 3 months | 2 months | 1 month | 2 weeks | 1 week | last weekend | Election Day
Candidate | Explore | file--bwt 9-3 months | Seek endorsements | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone/ beg for money | Walk/phone
Ballot committee/ coalition | Build coalition | Deal with legalities | Signature gathering/sig. Validatiion | Measure on Ballot | Seek endorsements | Beg for money | Beg for money | Beg for money | Beg for money | Beg for money | GOTV
Campaign manager |  | Hire | Plan | Poll if possible | Oversee plan execution | Supervise media production | Manage crisis | Manage crisis | Plan GOTV | Manage crisis | Voter protection
Media specialist |  |  | Hire
|  |  | Earned media from filing on | Web site | Earned media | Earned media | Earned media | Earned media | Earned media | Earned media | GOTV
[6 empty] | Direct mail, radio, TV, etc | Direct mail, radio, TV, etc | Direct mail, radio, TV, etc | Direct mail, radio, TV, etc |  | GOTV
Field |  |  | Hire lead staff | Acquire voter file | Find phones |  | Update voter file with new reg. |  | Print GOTV lists
|  |  |  | Sigs. in lieu of filing fee | Sigs. in lieu of filing fee
|  |  |  | Volunteer recruitment and internal db | Volunteer recruitment and internal db | Volunteer recruitment and internal db | Volunteer recruitment and internal db | Volunteer recruitment and internal db | Volunteer recruitment and internal db | Volunteer recruitment and internal db | GOTV
|  |  |  | Targeted voter registration | Targeted voter registration | Targeted voter registration | Targeted voter registration
[5 empty] | Voter ID: walk and phone | Voter ID: walk and phone | Voter ID: walk and phone | Voter ID: walk and phone | Voter ID: walk and phone | Voter ID: walk and phone
[5 empty] | base voters | unlikely voters | permanent absentees | unlikely voters | unlikely voters | all Ids
[9 empty] | Plan GOTV | GOTV | GOTV
Fundraising | Exploratory committee | Make it legal: PAC or candidate committee | Early money | Early money | Big Donors | House parties | All donors resolicited | All donors resolicited | All donors resolicited | GOTV | GOTV
NB: All dates are approximate. All localities have their own rules. MAKE SURE YOU LEARN THE LEGAL REQUIREMENTS THAT APPLY TO YOUR CAMPAIGN.